## Sheet1
| July | August | September | October | November | December | January | February | March | April | May | June
Election dates | November: General election
Legislative dates | August: BDRs due (legislators); September: BDRs due (agencies); December: BDRs due (legislators); February: 2017 legislative session
PROGRAM GOALS
Recognition | July: ~ ID buildings ~ Discuss & approve possible themes; August: ~ ID partners to create exhibits ~ Discuss & approve process (if any); September: Create exhibits ~ Partners present theme to NCFW?; January: Unveil exnibit in Vegas?; April: Unveil exhibit in CC on Day @ Legislature?
Study | July: ID area for study; August: Assign members of Junior Comm or interns to study; September: Conduct study Survey members of boards & commissions? Research independently? Draft report; January: ~Present draft of study to NCFW ~Present draft recommendations ~NCFW discuss and finalize recommendations; February: Finalize study; April: Present results at Day @ Legislature
Report | August: Workshop to: ~ categorize Focus Areas ~ prioritize Topics of Interest for Report Discuss options to complete report; September: Conduct study Use volunteers Use interns Use junior commissioners; December: Present draft report; January: Finalize report; February: Distribute report to legislators before session
Propose legislation | August: Discuss legislation clarifying the mission and duties of the Commission; September: Find bill sponsor; October: Submit BDR request; January: Write one page info sheet on BDR & distribute to legislators
|  | Review BDRs | Any priority areas that need legislation? | ID bill sponsor | Submit BDR | Develop guidance for education and/or advocacy by Commission | Adopt guidance for education / advocacy by Commission |  |  | Day @ Legislature
|  | Decide on a Commission for Women Day @ Legislature | Schedule Day @ Legislature | Request legislative support for Commission and make arrangements | Develop agenda for Day @ Legislature
OPERATIONAL GOALS
Work Plan | July: Workshop draft plan; August: ...Finalize plan for ...Commissioners take on speicific roles; September: Commissioners volunteer for tasks
Junior Commission | Raise issue of Junior Commission (approve?) | Design Junior Commission process & approve | Create Junior Commission & recruit | Appoint (?) Junior Commission |  |  | Reports from Junior Commissioners | Reports from Junior Commissioners | Reports from Junior Commissioners | ~ Day @ legislature…invite Junior Commissioners | Reports from Junior Commissioners
Fundraising | August: ~Finalize work plan ~Write case staement; September: ~Identify funding sources ~Divide up requests